## Assessment #4
DRAFT (subject to change at DOE's discretion)
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 |  |  | Week 13 | Week 14 | Week 15
Team 1 | Week 1: Prep Week; Week 2: Test Week; Week 3: Data Analysis (15 days); Week 12: Prep and Travel Day | Judging Panel Meeting | Travel Day | DOE Review and Approval (2 weeks) |  |  | Prep & Travel Day | Make announcement | Travel Day
Team 2 | Week 2: Prep Week; Week 3: Test Week; Week 4: Data Analysis (15 days)
Team 3 | Week 3: Prep Week; Week 4: Test Week; Week 5: Data Analysis (15 days)
Team 4 | Week 4: Prep Week; Week 5: Test Week; Week 6: Data Analysis (15 days)
Team 5 | Week 5: Prep Week; Week 6: Test Week; Week 7: Data Analysis (15 days)
Team 6 | Week 6: Prep Week; Week 7: Test Week; Week 8: Data Analysis (15 days)
Team 7 | Week 7: Prep Week; Week 8: Test Week; Week 9: Data Analysis (15 days)