## Plan
KEY DATES |  | SOCIAL MEDIA ACCOUNTS
Date | Description | Platform | NASA | PRI | TC | Hashtags
2014-03-10 | The announcement of the challenge is on March 10. The announcement will be made by a press release from NASA HQ, followed by amplification of the challenge at a SXSW panel. | Facebook | facebook.com/nasatechnology; facebook.com/nasa | facebook.com/PlanetaryResources | facebook.com/TopCoderInc | #AsteroidHunters
2014-03-17 | The kickoff of the ADH challenge (the first in the AGC series) will occur on 03/17/14. We will promote the kickoff of the contest through social media. | Twitter | twitter.com/asteroidgc | twitter.com/PLanetaryRsrcs | twitter.com/topcoder | #AsteroidHunters
|  | Google+ | https://plus.google.com/102901262565157821330/about | https://plus.google.com/104299149917517298353 | plus.google.com/+topcoder | #AsteroidHunters
Approvers |  | LinkedIn | N/A | linkedin.com/company/planetary-resources-inc- | linkedin.com/company/topcoder | N/A
AGC | Redacted Names | Website | nasa.gov | www.planetaryresources.com | N/A | N/A
ADH | Redacted Names | TopCoder Blog & News Feed | N/A | N/A | topcoder.com/blog/ & community.topcoder.com/tc | N/A
ANNOUNCEMENT MESSAGE |  | 3/10/2014 MEDIA PRODUCTS |  |  | AMPLIFICATION MEDIA PRODUCTS
Item | Description | Group | Product/Action |  | Group | Product/Action
Date | 2014-03-10 | NASA/PRI/TC | Press Release |  | NASA/PRI/TC | Social Media
Text Content | Be an asteroid hunter! A new NASA challenge with $35,000 in prizes kicks off on March 17. This NASA challenge will develop a moving object recognition algorithm to identify asteroids. Learn more and register at bit.ly/AsteroidHunters | NASA | ADH video posted on NASA YouTube & appropriate nasa.gov pages |  | NASA/PRI/NTL/TC | Possible media telecon on 3/17
Image Content | URL Removed | NASA/PRI/TC | Social Media |  | NASA/PRI/NTL/TC | Possible social media engagement
|  | NASA | Release repurposed as feature for front page of nasa.gov
KICKOFF MESSAGE
Item | Description | VIDEOS
Date | 2014-03-17 | Challenge | Description |  | Date
Text Content | Be an asteroid hunter! Visit www.topcoder.com/asteroids to learn how you can win $35,000 in prizes and help save our planet! Learn more and register at bit.ly/AsteroidHunters | AGC | Storyboard Delivery |  | 2014-02-20
Image Content | URL Removed |  | Storyboard Feedback Due |  | 2014-02-21
|  |  | Draft Video Delivery |  | 2014-02-28
ADDITIONAL AMPLIFICATION/PROMOTION EVENTS |  |  | Draft Video Feedback Due |  | 2014-03-03
Date | Description |  | Final Delivery of Video |  | 2014-03-07
3/11 - end of contest | Ongoing promotion of contest through social media and other events as appropriate | ADH | Script Delivery |  | 2014-02-20
Removed | Lunar Planetary Science Conference - Decision reached not an appropriate venue to announce |  | Script Feedback Due |  | 2014-02-24
2014-03-26 | Asteroid Initiative Opportunities Forum - promote challenge to general public |  | Storyboard Delivery |  | 2014-02-26
|  |  | Storyboard Feedback Due |  | 2014-02-28
| LIVE EVENT WITH LEADERSHIP (TBD) |  | Animation Delivery |  | 2014-03-03
Date | Description |  | Animation Feedback Due |  | 2014-03-04
2014-03-17 | Still in work, but a "live" event either media telecon or web-based Q&A with key individuals: including Redacted Names |  | Draft Video Delivery |  | 2014-03-07
|  |  | Draft Video Feedback Due |  | 2014-03-10
|  |  | Final Delivery of Video |  | 2014-03-14